## Sheet1
Project Cost Estimate
Prepared by: Abdelrahman Shemies | Date: | 2023-01-08
| # Units/Hrs. | Cost/Unit/Hr. | Subtotals | WBS Level 1 Totals | % of Total
WBS Items
1. Project Management |  |  |  | 278625 | 9.151%
1.1 Project manager | 900 | 100 | 90000
1.2 Project team members | 2500 | 75 | 187500
1.3 Meetings for stake holders | 9 | 125 | 1125
2.Requirements Gathering |  |  |  | 148000 | 4.861%
2.1 Meetings | 170 | 200 | 34000
2.2 Resources | 380 | 300 | 114000
3. Analysis and Design |  |  |  | 301500 | 9.902%
3.1 Create system and user interface designs | 300 | 600 | 180000
3.2 Develop database schema | 260 | 500 | 130000
3.3 Create prototype or mock-up of system | 400 | 600 | 240000
3.4 Develop technical documentation | 270 | 450 | 121500
4.Implementation |  |  |  | 774000 | 25.42%
4.1 Develop code for system and database | 300 | 600 | 180000
4.2 Integrate system components | 260 | 500
4.3 Procure hardware and software components | 400 | 600
4.4 Set up development environment | 270 | 450 | 594000
5. Hardware |  |  |  | 76000 | 2.496%
2.1 Editors and Reviewer devices | 100 | 600 | 60000
2.2 Servers | 4 | 4000 | 16000
3. Software |  |  |  | 681106.0898 | 22.37%
3.1 Website domain and email service | 1 | 2000 | 2000
3.2 On-Shelf software | 7 | 14000 | 98000
3.2 Software development* |  |  | 581106.0898
4. Testing (10% of total hardware and software costs) |  |  | 75710.609 | 75710.609 | 2.487%
5. Training and Support |  |  |  | 202400 | 6.647%
5.1 Trainee cost | 100 | 500 | 50000
5.2 Travel cost | 12 | 700 | 8400
5.3 Project team members | 1920 | 75 | 144000
6. Reserves (20% of total estimate) |  |  | 507468.3398 | 507468.3398 | 16.67%
Total project cost estimate |  |  |  | 3044810.0385
3.2 Software development
Contractor labor estimate | 3000 | 150 | 450000
Project team member estimate | 1920 | 75 | 144000
Total labor estimate |  |  | 594000
Function point estimate | Quantity | Conversion Factor | Function Points
External inputs | 10 | 4 | 40
External interface files | 3 | 7 | 21
External outputs | 3 | 5 | 15
External queries | 3 | 4 | 12
Logical internal tables | 6 | 10 | 60
Total function points |  |  | 148
Java 2 languange equivalency value |  |  | 46
Source lines of code (SLOC) estimate |  |  | 6808
Productivity *KSLOC^Penalty (person months) | 30.2659
Total labor hours (160 hours/month) | 4842.5507
Cost/labor hour ($120/hour) | 120
Total software development estimate | 581106.0898

## Sheet2
* Software development
Contractor labor estimate | 3000 | 150 | 450000
Project team member estimate | 1920 | 75 | 144000
Total labor estimate |  |  | 594000
Function point estimate | Quantity | Conversion Factor | Function Points
External inputs | 10 | 4 | 40
External interface files | 3 | 7 | 21
External outputs | 3 | 5 | 15
External queries | 3 | 4 | 12
Logical internal tables | 6 | 10 | 60
Total function points |  |  | 148
Java 2 languange equivalency value |  |  | 46
Source lines of code (SLOC) estimate |  |  | 6808
Productivity *KSLOC^Penalty (person months) | 30.2659
Total labor hours (160 hours/month) | 4842.5507
Cost/labor hour ($120/hour) | 120
Total software development estimate | 581106.0898